## Auto-updating Gantt chart
[5 empty] | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Task name | Task owner | Start date | End date | Duration | 2016-06-06 | 2016-06-07 | 2016-06-08 | 2016-06-09 | 2016-06-10 | 2016-06-11 | 2016-06-12
Project kick-off | Client | 2016-06-06 | 2016-06-07 | 2 | Client | Client | no | no | no | no | no
Brief signed off | Client | 2016-06-08 | 2016-06-10 | 3 | no | no | Client | Client | Client | no | no
Master English copywriting | Content team | 2016-06-13 | 2016-06-13 | 1 | no | no | no | no | no | no | no
Sub-editing | Content team | 2016-06-14 | 2016-06-16 | 3 | no | no | no | no | no | no | no
Client review (round 1) | Client | 2016-06-17 | 2016-06-20 | 2 | no | no | no | no | no | no | no
Take-in client amends | Content team | 2016-06-21 | 2016-06-21 | 1 | no | no | no | no | no | no | no
Client review (round 2) | Client | 2016-06-22 | 2016-06-23 | 2 | no | no | no | no | no | no | no
Take-in client amends | Content team | 2016-06-24 | 2016-06-24 | 1 | no | no | no | no | no | no | no
Master English signed off | Client | 2016-06-27 | 2016-06-27 | 1 | no | no | no | no | no | no | no
Localisation into DE, FR, ES & NORDICS | Localisation team | 2016-06-28 | 2016-07-11 | 10 | no | no | no | no | no | no | no
Local reviewer (round 1) | Client | 2016-07-12 | 2016-07-18 | 5 | no | no | no | no | no | no | no
Take in local reviewer amends | Localisation team | 2016-07-19 | 2016-07-21 | 3 | no | no | no | no | no | no | no
Local reviewer (round 2) | Client | 2016-07-22 | 2016-07-25 | 2 | no | no | no | no | no | no | no
Take in local reviewer amends | Localisation team | 2016-07-26 | 2016-07-27 | 2 | no | no | no | no | no | no | no
Client sign off | Client | 2016-07-28 | 2016-07-28 | 1 | no | no | no | no | no | no | no
Formulas:
Tuesday = [Monday]+1

## Holidays
2016 non-work days
2016-05-30
2016-08-29
2016-12-25
2016-12-27
2017-01-01
2017-01-02
2017-04-14
2017-04-17
2017-05-01
2017-05-29
2017-08-28
2017-12-25
2017-12-26
2018-01-01
2018-01-02